## Indicator Tracking
NERP file designed by Biju & updated as of 07.10.2015
Outcomes and Outputs | MOV/Target Indicators | Indicator Number ACT | Figures to date and as of final day of the the month
|  |  | Total to date | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
DCA Shelter Outcome:
Disaster affected people have access to safe and adequate temporary shelter and/or settlement based on the standard set and enabled them to either rehabilitate or reconstruct earthquake resistant permanent homes. | affected households benefited from shelter assistance as non-food items (NFI-plastic tarpaulin and tent) for maintaining a safe and adequate temporary shelter | 10000 | 7312 | Aug: 7305; Sep: 7305; Oct: 7
| families/target households benefited from cash support for constructing intermediate shelter. | 10000 | 11016 | Aug: 10516; Sep: 11016; Oct: 0
DCA Shelter Output:
9,000 affected families/households with due consideration to vulnerable families receive emergency shelter kits (tents/tarpaulin, rope, mat etc) | households receive emergency shelter kits (tents/tarpaulin, rope, mat etc) | 9000 | 7312 | Aug: 7305; Sep: 7305; Oct: 7
10,000 families/households are able to construct intermediate shelter with cash support. | households construct intermediate shelter with cash support. | 10000 | 11016 | Aug: 10516; Sep: 11016; Oct: 0
7,000 families targeted benefited by CGI sheets. | HHs targeted benefited by CGI sheets (now cash) | 7000 | 11016 | Aug: 10516; Sep: 11016; Oct: 0
DCA WASH Outcome – Water:
1. Beneficiaries have access to safe drinking water of sufficient quantity for drinking, cooking and maintaining personal and domestic hygiene, meeting Sphere standards | Up to 12,000 households (approximately 90,000 beneficiaries/individuals)) have access to safe and sufficient drinking water meeting Sphere standards. | 12000 | 5123 | Aug: 2922; Sep: 5123; Oct: 0
DCA Water Output:
Temporary water supply providing safe drinking water of sufficient quantity to the beneficiaries while repairing/rehabilitating water distribution networks. | HHs have safe drinking water minimum 15 litres per person. | 12000 | 5123 | Aug: 2922; Sep: 5123; Oct: 0
Repair/rehabilitation/construction of water distribution network. | # of temporary and permanent water distribution points constructed | tbc | 74 | Aug: 62; Sep: 74; Oct: 0
Ensure involvement of local municipalities/authorities in identification and selection of water distribution networks to be repaired/rehabilitated. | # of water distribution networks identified and repaired/rehabilitated | tbc | 74 | Aug: 62; Sep: 74; Oct: 0
12,000 households have safe drinking water minimum 15 litres per person. | Up to 12,000 households (approximately 90,000 individual/beneficiaries) have access to adequate sanitation facilities meeting Sphere Standards. | 12000 | 2894 | Aug: 2894; Sep: 2894; Oct: 0
# of temporary and permanent water distribution points constructed |  | tbc | 74 | Aug: 62; Sep: 74; Oct: 0
# of water distribution networks identified and repaired/rehabilitated |  | tbc | 74 | Aug: 62; Sep: 74; Oct: 0
DCA Sanitation Output 2 - Sanitation:
Outcome: Installation of temporary emergency latrines | (approximately 90,000 individual/beneficiaries) have access to latrine as per the standard of maximum 20 persons per latrine. | 12000 | 2894 | Aug: 2894; Sep: 2894; Oct: 0
2. Repair/rehabilitation/construction of communal/family latrines | households (approximately 90,000 individual/beneficiaries) have access to latrine as per the standard of maximum 20 persons per latrine. # of communal/family latrines repaired/rehabilitated/constructed | 12000 | 2894 | Aug: 2894; Sep: 2894; Oct: 0
| Individual permanent latrines built/repaired |  | 435 | Aug: 192; Sep: 435; Oct: 0
| Additional:emergency latrines |  | 154 | Sep: 154; Oct: 0
| School/insitutional latrines bilt/reparied |  | 77 | Aug: 77; Sep: 77; Oct: 0
3. Installation of hand shower and washing facilities close to latrines | # of showers/bathing places constructed |  | 1 | Aug: 1; Sep: 1; Oct: 0
Cross Cutting - through survey - PDM | 90 % of latrines repaired/rehabilitated/ constructed are equipped with hand washing facilities, one 1 liter mug and one 10 liter bucket for anal cleansing. | 90% | 10619 | Aug: 10170; Sep: 10619; Oct: 0
DCA WASH Outcome 3 – Hygiene:
Beneficiaries are aware of key WASH related health risks and take action to prevent these. | Up to 12,000 households (approximately 90,000 individual/beneficiaries) have access to adequate sanitation facilities meeting Sphere Standards. | 12000
Through KAP survey | 70% beneficiaries from the hygiene promotion program have increased knowledge about WASH related health risks and are able to take action to prevent these and to make optimal use of water and sanitation facilities. | KAP
DCA Hygiene Output 3:
1. Hygiene kits are distributed to beneficiaries | 1.1 # of hygiene kits are distributed to households | tbc | 10619 | Aug: 10170; Sep: 10619; Oct: 0
A hygiene promotion team is recruited and trained | 1.1 # hygiene promoters are recruited and trained | tbc | 169 | Aug: 41; Sep: 169; Oct: 0
Hygiene promotion awareness activities addressing major WASH related health risks are carried out by hygiene promoters and community mobilisers | 3.1 # of hygiene promotion activities carried out in target locations | tbc | 493 | Aug: 60; Sep: 493; Oct: 0
DCA Food Security Outcome:
Beneficiaries are able to meet household food needs, and reconstitute productive assets, in order to resume pre-crisis livelihoods. | 10,000 affected families receive food in line with sphere standard during the emergency period. | 10000 | 10498 | Aug: 10055; Sep: 10055; Oct: 443
DCA Food Security Output :
10,000 affected families receive food basket as per standard during the emergency period. | 1.1 List of identified affected and vulnerable families | Y/N
| 1.2 Distribution of food items to 10,000 affected families during the emergency period. | 10000 | 10101 | Aug: 9658; Sep: 9658; Oct: 443
| Families Reached through early recovery livelihoods assistance | n/a | 397 | Aug: 397; Sep: 397; Oct: 0
KAP is needed | 90 % of the beneficiaries express their satisfaction from the distribution and quality of food. | KAP
DCA Psychosocial Support Outcome:
Existing social, community, and family systems promote an environment for recovery and human development. | households/families benefit from psychosocial support by increasing their positive coping mechanisms and sense of security. | 27500 persons | 20433 | Aug: 10636; Sep: 20433; Oct: 0
DCA Psychosocial Support Output:
1. 5,000 affected families/households have access to community based psychosocial support. | 1.1 5,000 families provided with psychosocial support between May 2015 – April 2016. | 27500 persons | 10625 | Aug: 8217; Sep: 10625; Oct: 0
2. Community and family support networks (formal and informal groups) that provide protection, care, and psychosocial support for vulnerable earthquake-affected families are strengthened. | 1.1 25 community support networks (formal and informal groups) for protection, care, and psychosocial support (e.g. community self-help groups, sharing of childcare, women’s groups, youth groups etc.) in target areas from May 2015 – April 2016. | 25 | 12 | Aug: 3; Sep: 12; Oct: 0
| New: No Network members |  | 5419 | Aug: 556; Sep: 5419; Oct: 0
Safe spaces for women and children established and equipped. | 3.1 # of safe spaces for women and children established and equipped. | tbc | 15 | Aug: 14; Sep: 15; Oct: 0
Culturally appropriate recreational activities for girls, boys and adolescents organized in affected communities. | 4.1 Record of recreational activities organized targeting to specific groups. | tbc
| New: No of beneficiaries from recreational activities |  | 4111 | Aug: 1809; Sep: 4111; Oct: 0
ACT member staff and community/social workers and staff of partners trained in community based psychosocial support and/or psychological first aid. | Increased levels of knowledge on CBPS among participants. | KAP
| New: Number of ACT staff trained |  | 271 | Aug: 23; Sep: 271; Oct: 0
Referral systems for people in need of focused care/specialized mental health or protection services identified/established | List of referral hospitals / organizations providing focused care/specialized services per district and location. | Y/N
| New: Number of people referred |  | 7 | Aug: 0; Sep: 7; Oct: 0
Referral systems for people in need of focused care/specialized mental health or protection services identified/established | List of referral hospitals / organizations providing focused care/specialized services per district and location. | Y/N | Yes | Aug: Yes; Sep: Yes; Oct: No
| Gorkha | Y/N | No | bar: Aug to Oct
| Dhading | Y/N | Yes | Aug: Yes; Sep: Yes; Oct: No
| Baktapur | Y/N | No | bar: Aug to Oct
| Lalitpur | Y/N | No | bar: Aug to Oct

## Overview
NERP file designed by Biju & updated as of 07.10.2015
LOCAL IMPLEMENTING PARTNERS | SHELTER |  | WATER |  |  | SANITATION |  |  |  |  | HYGIENE |  |  |  | FOOD SECURITY / LIVELIHOOD |  |  | PROTECTION / PSYCHOSOCIAL SUPPORT (PSS)
| Indicator S1: NFI (Tarp, Blanket, Matt etcetera) for maintaining a safe and adequate temporary shelter. ACT Target: 10000 HH | Indicator S2: Families/target households benefited from cash support (USD 150) for constructing intermediate shelter. ACT Target: 10000 HH | Indicator W1: HHs have safe drinking water minimum 15 litres per person. ACT Target: 12000 HH | Indicator WX1 (Non ACT): Recorded # of emergency latrines | Indicator W2: # of Temporary and permanent water distribution points constructed ACT Target: tbc Indicator W3: # of water distribution networks identified and repaired/rehabilitated ACT Target: tbc | Indicator R1: approximately 90,000 individual/beneficiaries) have access to latrine as per the standard of maximum 20 persons per latrine. ACT Target: 12000 HH | Indicator R3: Individual permanent latrines built/repaired ACT Target: ? | Indicator R4: School/insitutional latrines bilt/reparied ACT Target: ? | Indicator R5: # of showers/bathing places constructed ACT Target: tbc | Indicator R6: 90 % of latrines repaired/rehabilitated/ constructed are equipped with hand washing facilities, one 1 liter mug and one 10 liter bucket for anal cleansing. ACT Target: tbc | Indicator H1: 70% beneficiaries from the hygiene promotion program have increased knowledge about WASH related health risks and are able to take action to prevent these and to make optimal use of water and sanitation facilities. ACT Target: tbc | Indicator H2: # of hygiene kits distributed to households ACT Target: tbc | Indicator H3: # of hygiene promoters are recruited and trained ACT Target: tbc | Indicator H4: # of hygiene promotion activities carried out in target locations ACT Target: tbc | Indicator L1: Distribution of food items to 10,000 affected families during the emergency period. ACT Target: 10000HH | Indicator L2: Early Recovery Livelihood Assistance ACT Target: NA | Indicator L3: 90% of beneficiaries express satisfaction ACT Target: tbc | Indicator P1: 5,000 affected families/households have access to community based psychosocial support. ACT Target: 27500 Persons | Indicator P2: Community and family support networks (formal and informal groups) that provide protection, care, and psychosocial support for vulnerable earthquake-affected families are strengthened. ACT Target: 25 | Indicator PX2 (Non ACT): # of beneficiaries for indicator P2 Target: tbc | Indicator P3: Safe spaces for women & children established equipped ACT Target: tbc | Indicator P4: Culturally appropriate recreational activities for girls, boys and adolescents organized in affected communities. ACT Target: tbc | (Non ACT) Indicator PX4: Recorded # of beneficiaries. Target: tbc | Indicator P5: Increased levels of knowledge on CBPS among participants. ACT Target: tbc | (ACT member staff and community/social workers and staff of partners trained in community based psychosocial support and/or psychological first aid. Target: tbc | Indicator P6: Referral systems for people in need of focused care/specialized mental health or protection services identified/established ACT Target: tbc
ECO-Nepal (Gorkha) | 2825 | 2448 | 617 | 154 | 13 | 2820 | 0 | 11 | 1 | 3843 | KAP | 3843 | 56 | 7 | 2552 | 397 | 0 | 0 | 0 | 175 | 0 | 4 | 69 | KAP | 8 | 0
FAYA-Nepal (Dhading) | 4480 | 4874 | 1893 | 0 | 53 | 0 | 0 | 48 | 0 | 5079 | KAP | 5079 | 82 | 378 | 4480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KAP | 0 | 0
FSCN (LTP & BKT) | 0 | 3694 | 2613 | 0 | 8 | 74 | 435 | 18 | 0 | 1697 | KAP | 1697 | 31 | 108 | 2626 | 0 | 0 | 49 | 9 | 191 | 6 | 35 | 1025 | KAP | 69 | 0
WOREC (LTP & BKT) | 234 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 443 | NA | NA | 3028 | 0 | 4437 | 0 | 0 | 576 | KAP | 156 | 7
POURAKHI (Dhading) | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 7548 | 3 | 616 | 9 | 64 | 2441 | KAP | 38 | 0
TOTAL ACHIEVED | 7312 | 11016 | 5123 | 154 | 74 | 2894 | 435 | 77 | 1 | 10619 | KAP | 10619 | 169 | 493 | 10101 | 397 | 0 | 10625 | 12 | 5419 | 15 | 103 | 4111 | KAP | 271 | 7
ACT TARGET | 10000 | 10000 | 12000 | tbc | tbc | 12000 | tbc | tbc | tbc | tbc | KAP | tbc | tbc | tbc | 10000 | tbc | KAP | 27500 | 25 | tbc | tbc | tbc | tbc | tbc | tbc | tbc
PROGRESS | 73.12% | 110.16% | 42.69% | tbc | tbc | 24.12% | tbc | tbc | tbc | tbc | KAP | tbc | tbc | tbc | 101.01% | tbc | KAP | 38.64% | 48% | tbc | tbc | tbc | tbc | tbc | tbc | tbc

## ECO-Nepal (Gorkha)
NERP file designed by Biju & updated as of 07.10.2015
Note: Comments & Clarifications are made in the footnotes for the colored content of the cells of respective columns.
VDC/Municipality | SHELTER |  |  |  |  | WATER | [5 empty] | SANITATION | [6 empty] | HYGIENE | [8 empty] | FOOD SECURITY / LIVELIHODD | [5 empty] | PROTECTION / PSYCHOSOCIAL SUPPORT
| Indicator S1: NFI (Tarp, Blanket, Matt etcetera) for maintaining a safe and adequate temporary shelter. ACT Target: 10000 HH |  |  |  | Indicator S2: Families/target households benefited from cash support (USD 150) for constructing intermediate shelter. ACT Target: 10000 HH | Indicator W1: HHs have safe drinking water minimum 15 litres per person. ACT Target: 12000 HH |  |  | Indicator WX1 (Non ACT): Recorded # of emergency latrines | Indicator W2: # of Temporary and permanent water distribution points constructed ACT Target: tbc Indicator W3: # of water distribution networks identified and repaired/rehabilitated ACT Target: tbc |  | Indicator R1: approximately 90,000 individual/beneficiaries) have access to latrine as per the standard of maximum 20 persons per latrine. ACT Target: 12000 HH |  | Indicator R3: Individual permanent latrines built/repaired ACT Target: ? | Indicator R4: School/insitutional latrines bilt/reparied ACT Target: ? |  | Indicator R5: # of showers/bathing places constructed ACT Target: tbc | Indicator R6: 90 % of latrines repaired/rehabilitated/ constructed are equipped with hand washing facilities, one 1 liter mug and one 10 liter bucket for anal cleansing. ACT Target: tbc | Indicator H1: 70% beneficiaries from the hygiene promotion program have increased knowledge about WASH related health risks and are able to take action to prevent these and to make optimal use of water and sanitation facilities. ACT Target: tbc | Indicator H2: # of hygiene kits distributed to households ACT Target: tbc |  |  | Indicator H3: # of hygiene promoters are recruited and trained ACT Target: tbc |  |  |  | Indicator H4: # of hygiene promotion activities carried out in target locations ACT Target: tbc | Indicator L1: Distribution of food items to 10,000 affected families during the emergency period. ACT Target: 10000HH |  |  | Indicator L2: Early Recovery Livelihood Assistance ACT Target: NA |  | Indicator L3: 90% of beneficiaries express satisfaction ACT Target: tbc | Indicator P1: 5,000 affected families/households have access to community based psychosocial support. ACT Target: 27500 Persons | [9 empty] | Indicator P2: Community and family support networks (formal and informal groups) that provide protection, care, and psychosocial support for vulnerable earthquake-affected families are strengthened. ACT Target: 25 |  |  |  |  | (Non ACT) Indicator PX2: Recorded # of Network members. Target: tbc |  |  |  | Indicator P3: Safe spaces for women & children established equipped ACT Target: tbc | Indicator P4: Culturally appropriate recreational activities for girls, boys and adolescents organized in affected communities. ACT Target: tbc |  |  | (Non ACT) Indicator PX4: Recorded # of beneficiaries |  |  | Indicator P5: Increased levels of knowledge on CBPS among participants. ACT Target: tbc | (ACT member staff and community/social workers and staff of partners trained in community based psychosocial support and/or psychological first aid. Target: tbc | Indicator P6: Referral systems for people in need of focused care/specialized mental health or protection services identified/established ACT Target: tbc
| HH Covered (C4+D4+E4) | Tarpaulins | Blanket | Mattress | HH Covered | HH Covered | # of Temporary Water Schemes | # of Permanent Water Schemes | # emergency latrines | # of Temporary Water Schemes | # of Permanent Water Schemes | # of Emergency Latrines (WASH-Kits) | # of Temporary Latrines HH | # of Permanent Latrines for HH | # of Emergency Latrines (WASH-Kits) in school | # of latrines institutional | # constructed | HH Covered (Receiver's of Hygiene Kits) | Focus Group Discussions conducted & prelimary report writing ongoing | HH Covered (S) | Hygiene Kits | Hygiene Kit Replenishment | Recruited | # Trained partner staffs (including social mobilizers, PSS staffs) | # of school teachers trained | # of FCHV trained | # of Activities | HH Covered (AE+AF) | HH Covered (with food basket) | MPG Disbursement | HH Covered | MPG Disbursement | ?-KAP | Total # of Beneficiaries | Total # of sessions | # of Individual Counselling Sessions | # of Individual counselling Beneficiaries | # of Family Counselling Sessions | # of Family Counselling Beneficiaries | # Group Counselling sessions | # of Group Counselling Beneficiaries | # of Motivational Sessions & awareness on CBPS to school students | # of beneficiaries for motivational sessions & awareness on CBPS to school students | Networks Formed | # of TOT sessions to school teachers | # of sessions on awareness & orientation to teachers on PSS | # of sessions on Awareness to youth on CBPS | # of sessions on Awareness & orientation on CBPS to woman group | # of beneficiaries from TOT to school teachers | # of beneficiaries from awareness & orientation to teachers on PSS | # of beneficiaries from Awareness to youth on CBPS | # of beneficiaries from Awareness & orientation on CBPS to woman group | # of Spaces Established | # of RA for women | # of RA for school children | # of RA for youth | # of beneficiaries from RA for women | # of beneficiaries from RA for School Children | # of beneficiaries from RA for Youth | KAP Survey | # Partner Staffs trained | # of people referred for PSS/Protection Issues
Gorkha Mun. | 2144 | 2144 | 0 | 0 | 0 | 121 | 1 | 1 | 16 | 1 | 1 | 8 | 0 | 0 | 6 | 1 | 0 | 151 |  | 151 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 195 | 0 | 0 | 0 | ?-KAP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 30 | 56 | 89 | 0 | 0 | 4 | 0 | 0 | 69 | 0 |  | 8 | 0
Baguwa | 0 | 0 | 0 | 0 | 596 | 0 | 2 | 2 | 30 | 2 | 2 | 29 | 0 | 0 | 0 | 0 | 1 | 595 |  | 595 | 595 | 539 | 2 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | ?-KAP
Tanglichowk | 0 | 0 | 0 | 0 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 848 |  | 848 | 848 | 848 | 2 | 2 | 9 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | ?-KAP
Makaisingh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 653 |  | 653 | 653 | 653 | 2 | 2 | 7 | 9 | 2 | 187 | 0 | 187 | 187 | 187 | ?-KAP
Dhawa | 150 | 150 | 0 | 0 | 1026 | 210 | 4 | 2 | 18 | 4 | 2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1047 | 2 | 2 | 6 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | ?-KAP
Prtihbinarayan NP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 |  | 175 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ?-KAP
Darbung | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 885 |  | 885 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ?-KAP
Lho | 275 | 275 | 275 | 275 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 20 | 0 | 0 | 2 | 0 | 0 | 279 |  | 279 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0 | 0 | 0 | ?-KAP
Prok | 256 | 256 | 256 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ?-KAP
Saurpani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412 | 412 | 0 | 0 | 0 | ?-KAP
Simjong | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 291 | 291 | 0 | 0 | 0 | ?-KAP
Barpak | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 325 | 0 | 0 | 0 | ?-KAP
Hansapur | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1036 | 1036 | 0 | 0 | 0 | ?-KAP
Chhekempar | 0 | 0 | 0 | 0 | 0 | 286 | 1 | 0 | 16 | 1 | 0 | 14 | 0 | 0 | 2 | 0 | 0 | 257 |  | 257 | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 257 | 257 | 0 | 0 | 0 | ?-KAP
Aru Chanaute | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ?-KAP
Tandrang | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ?-KAP
Samagaun | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 0 | 210 | 210 | 210 | ?-KAP
| Total Households covered for indicator S1: 2825 |  |  |  | Total Households covered for indicator S2: 2448 | Total Households covered for indicator W1, W2 & W3: 617 |  |  | Total #s covered for indicator WX1:154 | Total # of covered for indicator W2 & W3: 13 |  | Total Households covered for indicator R1 & R2: 2820 |  | Total # built/repaired for indicator R3: 0 | Total # built/repaired for indicator R4: 11 |  | Total # built/repaired for indicator R5: 1 | Total # of HK distributed for indicator R6: 3843 |  | Total # of HK distributed for indicator H2: 3843 |  |  | Total # Trained for indicator H3:56 |  |  |  | Total # Trained for indicator H4: 7 | Total # Trained for indicator L1: 2552 |  |  | Total HH covered for indicator L3: 397 |  | 0 | Total # of beneficiaries covered for indicator P1: 0 | [9 empty] | Total networks formed for indicator P2: 0 |  |  |  |  | Total # of beneficiaries for indicator PX2: 175 |  |  |  | Total spaces created for indicator P3: 0 | Total # of RA for indicator P4: 4 |  |  | Total # of beneficiaries for indicator PX4: 69 |  |  | KAP Survey | Total # trained for Indicator PX5: 8 | Total # for indicator P6: 0
Foornotes: Gorkha Municipality = Ward 1 - 6 | Footnotes: 2 Blankets, 2 Mattresses & 1 Tarp per Household | [10 empty] | Footnotes: Total HH for indicator R1&R2 = (# of emergency latrines + # of temp. latrines) * 20 persons | [15 empty] | Footnotes: Unconditional & Multi Purpose Grant for People in GON's Social Welfare List.

## FAYA-Nepal (Dhading)
NERP file designed by Biju & updated as of 07.10.2015
Note: Comments & Clarifications are made in the footnotes for the colored content of the cells of that column.
VDC/Municipality | SHELTER |  |  |  |  | WATER | [5 empty] | SANITATION | [6 empty] | HYGIENE | [9 empty] | FOOD SECURITY / LIVELIHOOD |  |  |  |  | Protection / Psychosocial Support (PSS)
| Indicator S1: NFI (Tarp, Blanket, Matt etcetera) for maintaining a safe and adequate temporary shelter. ACT Target: 10000 HH |  |  |  | Indicator S2: Families/target households benefited from cash support (USD 150) for constructing intermediate shelter. ACT Target: 10000 HH | Indicator W1: HHs have safe drinking water minimum 15 litres per person. ACT Target: 12000 HH |  |  | Indicator WX1 (Non ACT): Recorded # of emergency latrines | Indicator W2: # of Temporary and permanent water distribution points constructed ACT Target: tbc Indicator W3: # of water distribution networks identified and repaired/rehabilitated ACT Target: tbc |  | Indicator R1: approximately 90,000 individual/beneficiaries) have access to latrine as per the standard of maximum 20 persons per latrine. ACT Target: 12000 HH |  | Indicator R3: Individual permanent latrines built/repaired ACT Target: ? | Indicator R4: School/insitutional latrines bilt/reparied ACT Target: ? |  | Indicator R5: # of showers/bathing places constructed ACT Target: tbc | Indicator R6: 90 % of latrines repaired/rehabilitated/ constructed are equipped with hand washing facilities, one 1 liter mug and one 10 liter bucket for anal cleansing. ACT Target: tbc | Indicator H1: 70% beneficiaries from the hygiene promotion program have increased knowledge about WASH related health risks and are able to take action to prevent these and to make optimal use of water and sanitation facilities. ACT Target: tbc | Indicator H2: # of hygiene kits distributed to households ACT Target: tbc |  |  | Indicator H3: # of hygiene promoters are recruited and trained ACT Target: tbc |  |  |  | Indicator H4: # of hygiene promotion activities carried out in target locations ACT Target: tbc | Indicator L1: Distribution of food items to 10,000 affected families during the emergency period. ACT Target: 10000HH |  |  | Indicator L2: Early Recovery Livelihood Assistance ACT Target: NA |  | Indicator L3: 90% of beneficiaries express satisfaction ACT Target: tbc | Indicator P1: 5,000 affected families/households have access to community based psychosocial support. ACT Target: 27500 Persons | [9 empty] | Indicator P2: Community and family support networks (formal and informal groups) that provide protection, care, and psychosocial support for vulnerable earthquake-affected families are strengthened. ACT Target: 25 |  |  |  |  | (Non ACT) Indicator PX2: Recorded # of Network members. Target: tbc |  |  |  | Indicator P3: Safe spaces for women & children established equipped ACT Target: tbc | Indicator P4: Culturally appropriate recreational activities for girls, boys and adolescents organized in affected communities. ACT Target: tbc |  |  | (Non ACT) Indicator PX4: Recorded # of beneficiaries |  |  | Indicator P5: Increased levels of knowledge on CBPS among participants. ACT Target: tbc | (Non ACT) Indicator PX5: Recorded # of Partner staff trained | Indicator P6: Referral systems for people in need of focused care/specialized mental health or protection services identified/established ACT Target: tbc
| HH Covered (C4+D4+E4) | Tarpaulins | Blanket | Mattress | HH Covered | HH Covered | # of Temporary Water Schemes | # of Permanent Water Schemes | # emeregency latrines | # of Temporary Water Schemes | # of Permanent Water Schemes | # of Emergency Latrines (WASH-Kits) | # of Temporary Latrines, HH | # Constructed | # of Emergency Latrines (WASH-Kits) in School | # of Latrines Institutional | # constructed | HH Covered (Receiver's of Hygiene Kits) | Focus Group Discussions conducted & prelimary report writing ongoing | HH Covered (S) | Hygiene Kits | Hygiene Kit Replenishment | # Recruited | # of Trained partner staffs (including social mobilizers, PSS staffs) | # of school teachers trained | # of FCHV trained | # of Activities | HH Covered(AB+AC) | MPG Disbursement | HH Covered (with Food basket) | HH Covered | MPG Disbursement | ?-KAP | Total # of Beneficiaries | Total # of sessions | # of Individual Counselling sessions | # of beneficiaries from indivdual counselling | # of family counselling sessions | # of beneficiaries from family counselling | # of group counselling sessions | # of beneficiaries from Group Counselling | # of motivational sessions & awareness on CBPS to school students | # of beneficiaries from motivational sessions & awareness on CBPS to school students | Networks Formed | # of sessions for TOT to School Teachers | # of sessions for Awareness & orientation to teachers on PSS | # of sessions for Awareness to youth on CBPS | # of sessions for Awareness & orientation on CBPS to woman group | # of beneficiaries from TOT to school teachers | # of beneficiaries from awareness & orientation to teachers on PSS | # of beneficiaries from Awareness to youth on CBPS | # of beneficiaries from Awareness & orientation on CBPS to woman group | # of Spaces Established | # of RA for Women | # of RA for School Children | # of RA for Youth | # of beneficiaries from RA for women | # of beneficiaries from RA for School Children | # of beneficiaries from RA for Youth | KAP Survey | # of Partner Staffs trained | # of people referred for PSS/Protection Issues
Khari | 1202 | 1202 | 1202 | 0 | 1309 | 1011 | 1 | 26 | 0 | 1 | 26 | 0 | 0 | 0 | 14 | 0 | 0 | 1325 |  | 1325 | 1325 | 1316 | 3 | 4 | 10 | 9 | 129 | 1202 | 0 | 1202 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | KAP Survey | 6 | 0
Nalang | 1208 | 1208 | 1208 | 0 | 2208 | 534 | 0 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 16 | 0 | 0 | 2325 |  | 2325 | 2325 | 2302 | 3 | 4 | 15 | 8 | 117 | 2070 | 0 | 2070
Salang | 2070 | 2070 | 2070 | 0 | 1357 | 348 | 0 | 14 | 0 | 0 | 14 | 0 | 0 | 0 | 18 | 0 | 0 | 1429 |  | 1429 | 1429 | 1418 | 3 | 4 | 11 | 8 | 132 | 1208 | 0 | 1208
| Total Households covered for Indicator S1: 4480 |  |  |  | Total Households covered for Indicator S2: 4874 | Total Households covered for indicator W1, W2, & W3: 1893 |  |  | Total #s covered for indicator WX1: 0 | Total # covered for indicator W2, & W3: 53 |  | Total Households covered for indicator R1 & R2: 0 |  | # constructed for indicator R3: 0 | Total # buildt/repaired for indicator R4: 48 |  | # constructed for indicator R5: 0 | Total Households covered for indicator R6: 5079 |  | Total # of HK distribuited for indicator H2: 5079 |  |  | Total # Trained for indicator H3:82 |  |  |  | Total # Trained for indicator H4: 378 | Total # Trained for indicator L1: 4480 |  |  | Total HH covered for indicator L3: 0 |  | 0 | Total # of beneficiaries covered for indicator P1: 0 | [9 empty] | Total networks formed for indicator P2: 0 |  |  |  |  | Total # of beneficiaries for indicator PX2: 0 |  |  |  | Total spaces created for indicator P3: 0 | Total # of RA for indicator P4: 0 |  |  | Total # of beneficiaries for indicator PX4: 0 |  |  | KAP Survey | Total # trained for Indicator PX5: 6 | Total # for indicator P6: 0

## FSCN (LTP & BKT)
NERP file designed by Biju & updated as of 07.10.2015
VDC/Municipality |  | SHELTER |  |  |  |  | WATER | [5 empty] | SANITATION | [6 empty] | HYGIENE | [8 empty] | FOOD SECURITY / LIVELIHOOD | [7 empty] | PROTECTION / PYSCHOSOCIAL
|  | Indicator S1: NFI (Tarp, Blanket, Matt etcetera) for maintaining a safe and adequate temporary shelter. ACT Target: 10000 HH |  |  |  | Indicator S2: Families/target households benefited from cash support (USD 150) for constructing intermediate shelter. ACT Target: 10000 HH | Indicator W1: HHs have safe drinking water minimum 15 litres per person. ACT Target: 12000 HH |  |  | Indicator WX1 (Non ACT): Recorded # of emergency latrines | Indicator W2: # of Temporary and permanent water distribution points constructed ACT Target: tbc Indicator W3: # of water distribution networks identified and repaired/rehabilitated ACT Target: tbc |  | Indicator R1: approximately 90,000 individual/beneficiaries) have access to latrine as per the standard of maximum 20 persons per latrine. ACT Target: 12000 HH Indicator R2: approximately 90,000 individual/beneficiaries) have access to latrine as per the standard of maximum 20 persons per latrine. # of communal/family latrines repaired/rehabilitated/constructed ACT Target: 12000HH |  | Indicator R3: Individual permanent latrines built/repaired ACT Target: ? | Indicator R4: School/insitutional latrines bilt/reparied ACT Target: ? |  | Indicator R5: # of shower & bathing place constructed ACT Target: tbc | Indicator R6: 90 % of latrines repaired/rehabilitated/ constructed are equipped with hand washing facilities, one 1 liter mug and one 10 liter bucket for anal cleansing. | Indicator H1: 70% beneficiaries from the hygiene promotion program have increased knowledge about WASH related health risks and are able to take action to prevent these and to make optimal use of water and sanitation facilities. | Indicator H2: # of hygiene kits distributed to households ACT Target: tbc |  |  | Indicator H3: # of hygiene promoters are recruited and trained ACT Target: tbc |  |  |  | Indicator H4: # of hygiene promotion activities carried out in target locations ACT Target: tbc | Indicator L1: Distribution of food items to 10,000 affected families during the emergency period. ACT Target: 10000HH |  |  | Indicator L3: Early Recovery Livelihood Assistance ACT Target: NA |  | Indicator L4: 90% of beneficiaries express satisfaction ACT Target: tbc | Indicator P1: 5,000 affected families/households have access to community based psychosocial support. ACT Target: 5000HH | [9 empty] | Indicator P2: Community and family support networks (formal and informal groups) that provide protection, care, and psychosocial support for vulnerable earthquake-affected families are strengthened. ACT Target: 25 |  |  |  |  | (Non ACT) Indicator PX2: Recorded # of Network members. Target: tbc |  |  |  | Indicator P3: # of safe spaces for women and children established and equipped. ACT Target: tbc | Indicator P4: Culturally appropriate recreational activities for girls, boys and adolescents organized in affected communities. ACT Target: tbc |  |  | (Non ACT) Indicator PX4: Recorded # of beneficiaries for indicator P4 |  |  | Indicator P5: Increased levels of knowledge on CBPS among participants. ACT Target: tbc | (ACT member staff and community/social workers and staff of partners trained in community based psychosocial support and/or psychological first aid. Target: tbc |  | Indicator P6: Referral systems for people in need of focused care/specialized mental health or protection services identified/established ACT Target: ?
|  | HH Covered (C4+D4+E4) | Tarpaulins | Blanket | Mattress | HH Covered | HH Covered | # of Temporary Water Schemes | # of Permanent Water Schemes | # emergeny latrines | # of Temporary Water Schemes | # of Permanent Water Schemes | # of emergency latrines (WASH-Kits) | # of Temporary Latrines, HH | # Constructed | # of Emergency Latrines (WASH-Kits) in School | # of Latrines Institutional | # Constructed | HH Covered (Receiver's of Hygiene Kits) | Focus Group Discussions conducted & prelimary report writing ongoing | HH Covered (S) | Hygiene Kits | Hygiene Kit Replenishment | # Recruited | # of Trained partner staffs (including social mobilizers, PSS staffs) | # of school teachers trained | # of FCHV trained | # of Activities | HH Covered (AD+AE) | MPG Disbursement | HH Covered (with Food Basket) | HH Covered (AG) | MPG Disbursement | ?-KAP | Total # of Beneficiaries | Total # of sessions | # of Individual Counselling sessions | # of beneficiaries from individual counselling | # of family counselling sessions | # of beneficiaries from family counselling | # of group counselling sessions | # beneficaries from group counselling | # of motivational sessions & awareness on CBPS to school students | # of beneficaries from Motivational sessions & awareness on CBPS to school students | Networks formed | # of TOT sessions to School teachers | # of sessions on awareness and orientation to teachers on pss | # of sessions on awareness to youth group on CBPS | # of sessions on awareness and orientations on CBPS tp womens group | # of beneficiaries from TOT to school teachers | # of beneficiaries from awareness & orientation to teachers on PSS | # of beneficiaries from Awareness to youth on CBPS | # of beneficiaries from Awareness & orientation on CBPS to woman group | # of Spaces Established | RA for Women | RA for School Children | RA for Youth | # of beneficiaries from RA for women | # of beneficiaries from RA for School Children | # of beneficiaries from RA for Youth | KAP Survey | Partner staffs trained | workshop | Number of people referred for PSS/Protection Issues
Bhaktapur | Mahamanjushree | 0 | 0 | 0 | 0 | 657 | 400 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 36 | 0 | 4 | 0 | 216 |  | 216 | 216 | 216 | 6 | 12 | 13 | 0 | 73 | 25 | 0 | 25 | 0 | 0 |  | 36 | 10 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 1 | 0 | 26 | 9 | 10 | 0 | 2 | 9 | 12 | 2 | 395 | 354 | 77 | KAP | 0 | 0 | 0
| Changunaryan | 0 | 0 | 0 | 0 | 491 | 110 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 29 | 0 | 3 | 0 | 615 |  | 615 | 615 | 519 |  |  |  | 0 | 11 | 50 | 0 | 50 | 0 | 0
| Nekoshera | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | 125 | 0 | 125 | 0 | 0
| Sudal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 110 | 0 | 110 | 0 | 0
| Thathali | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 187 |  | 187
| Brahamani | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 181 | 0 | 181 | 0 | 0
| Kamalasi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 159 | 0 | 159 | 0 | 0
| Chareli | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 103 | 0 | 103 | 0 | 0
| Sukuldhoka, Golmadi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 26 | 0 | 26 | 0 | 0
| Bidol Sudal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 20 | 0 | 20 | 0 | 0
| Bageswori | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 25 | 0 | 25 | 0 | 0
| Telkot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 45 | 0 | 45 | 0 | 0
| Chaling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Dhuwakot | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 25 | 0 | 25 | 0 | 0
| Jagathi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lalitpur | Siddhipur | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 246 |  | 246 | 246 | 269 |  |  |  | 10 | 3 | 0 | 0 | 0 | 0 | 0 |  | 13 | 5 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 1 | 1 | 4 | 0 | 24 | 10 | 112 | 0 | 4 | 4 | 7 | 1 | 155 | 430 | 44 | KAP | 10 | 59 | 0
| Lubhu | 0 | 0 | 0 | 0 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 62 |  | 62 | 62 | 62 |  |  |  | 10 | 5 | 0 | 0 | 0 | 0 | 0
| Lamatar | 0 | 0 | 0 | 0 | 1304 | 137 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 249 | 0 | 0 | 0 | 408 |  | 408 | 408 | 412 |  |  |  | 0 | 3 | 200 | 0 | 200 | 0 | 0
| Bungmati | 0 | 0 | 0 | 0 | 0 | 1907 | 1 | 1 | 0 | 1 | 1 | 0 | 74 | 91 | 0 | 5 | 0 | 150 |  | 150 | 150 | 300 |  |  |  | 0 | 3 | 0 | 0 | 0 | 0 | 0
| Jharuwarasi | 0 | 0 | 0 | 0 | 492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 1 | 200 | 0 | 200 | 0 | 0
| Imadol Mahalaxmi Mun. | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 3 | 145 | 0 | 145 | 0 | 0
| Sankhu | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 200 | 0 | 200 | 0 | 0
| Ikutol | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 200 | 0 | 200 | 0 | 0
| Dalchoki | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 200 | 0 | 200 | 0 | 0
| Bisankhunarayan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 200 | 0 | 200 | 0 | 0
| Thuladurlung | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 200 | 0 | 200 | 0 | 0
| Lakuribhanjyang | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Lagankhel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Harisiddhi | [5 empty] | 59 |  | 1 | 0 | 0 | 1 | [8 empty] | 0 | 0 |  |  |  |  | 0 | 5
| Khokana | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Households covered for indicator S1: 0 |  |  |  | Total Households covered for indicator S2: 3694 | Total Households covered for indicator W1, W2, &W3: 2613 |  |  | Total #s covered for indicator WX1: 0 | Total # covered for indicator W2, &W3: 8 |  | # constructed/repaired for indicator R1&R2: 74 |  | # constructed for indicator R3: 435 | Total # built/repaired for indicator R4:18 |  | # constructed for indicator R5: 0 | Total Households covered for indicator R6: 1697 |  | Total # of HK distributed for indicator H2: 1697 |  |  | Total # Trained for indicator H3:31 |  |  |  | Total # Trained for indicator H4: 108 | Total # Trained for indicator L1: 2626 |  |  | Total HH covered for indicator L3: 0 |  | 0 | Total # of beneficiaries covered for indicator P1: 49 | [9 empty] | Total networks formed for indicator P2: 9 |  |  |  |  | Total # of beneficiaries for indicator PX2: 191 |  |  |  | Total spaces created for indicator P3: 6 | Total # of RA for indicator P4: 35 |  |  | Total # of beneficiaries for indicator PX4: 1025 |  |  | KAP Survey | Total # trained for indicator PX5: 69 |  | Total # for indicator P6: 0
187

## WOREC LTP & BKT)
NERP file designed by Biju & updated as of 07.10.2015
District | Shelter | [5 empty] | Food Security |  |  | Protection / Psychosocial Support (PSS)
| Indicator S1: NFI (Tarp, Blanket, Matt etcetera) for maintaining a safe and adequate temporary shelter. ACT Target: 10000 HH | [5 empty] | Indicator L1: Distribution of food items to 10,000 affected families during the emergency period. ACT Target: 10000HH |  |  | Indicator P1: 5,000 affected families/households have access to community based psychosocial support. ACT Target: 5000HH | [9 empty] | Indicator P2: Community and family support networks (formal and informal groups) that provide protection, care, and psychosocial support for vulnerable earthquake-affected families are strengthened. ACT Target: 25 | [5 empty] | (Non ACT) Indicator P2X: Recorded # of network members for indicator P2 Target: tbc |  |  |  |  | Indicator P3: # of safe spaces for women and children established and equipped. ACT Target: tbc | Indicator P4: Culturally appropriate recreational activities for girls, boys and adolescents organized in affected communities. ACT Target: tbc |  |  | (Non ACT) Indicator PX4: Recorded # of beneficiaries for indicator P4 Target: tbc |  |  | Indicator P5: Increased levels of knowledge on CBPS among participants. ACT Target: tbc | (ACT member staff and community/social workers and staff of partners trained in community based psychosocial support and/or psychological first aid. Target: tbc | [6 empty] | Indicator P6: Referral systems for people in need of focused care/specialized mental health or protection services identified/established ACT Target: ?
| # of HH benefited from NFI | Blanket | Mattress | Cloth | Kichen Utensils | Tarpaulin | # of HH benefited from Rice (kg) @ 5kg per HH for food basket | # of HH benefited from Baby feed - to PLW - food basket | # of HH benefited from Ready-to-eat Rice | Total # of Beneficiaries | Total # of sessions | # of individual counselling sessions | # of beneficiaries from individual counselling | # of family counselling sessions | # beneficiaries from of Family Counselling | # of group counselling sessions | # of beneficiaries from Group Counselling | # of motivational sessions & awareness on CBPS to school students | # of beneficiaries from Motivational Sessions & awareness on CBPS to school students | # of Networks Established | ToT to school teachers | Awareness & orientation to teachers on PSS | Awareness to youth groups on CBPS | Awareness on HH & GBV | Awareness & orientation on CBPS to women group | # of beneficiaries from ToT to school teachers | # of beneficiaries form Awareness & orientation to teachers on PSS | # of beneficiaries from Awareness to youth groups on CBPS | # beneficiaries orientation on HH & GBV | # beneficiaries from Awareness & orientation on CBPS to women group | # of Spaces Established | RA for Women | RA for School Children | RA for Youth | # of beneficiaries from RA for women | # of beneficiaries from RA for school children | # of beneficiaries from RA for Youth | KAP | # of Partner staffs trained | # trained on PFA | #trained in leadership | # trained in Curd Making Training | # trained in Agricultural Training | # trained in Velvet Shoe Making Training | # trained in knitting training | # of people referred for PSS/Protection Issues
Bhaktapur | 204 | 4 | 2 | 196 | 1 | 1 | 158 | 65 | 2 | 2315 | 0 | 0 | 193 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3159 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 0 |  | 0 | 21 | 18 | 5 | 20 | 20 | 0 | 7
Lalitpur | 30 | 24 | 1 | 0 | 1 | 4 | 125 | 95 | 16 | 713 | 0 | 0 | 134 | 0 | 0 | 0 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1278 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 0 |  | 0 | 7 | 7 | 14 | 22 | 0 | 22 | 0
| Total # of HHs benifited for indicator L1: 234 | [5 empty] | Total # of HHs benifited for indicator L1: 443 |  |  | Total # of beneficiaries for indicator P1: 3028 | [9 empty] | Total networks formed for indicator P2: 0 | [5 empty] | Total # of beneficiaries for indicator PX2: 4437 |  |  |  |  | Total # of spaces created for indicator P3: 0 | Total # of activities conducted for indicator P4: 0 |  |  | Total # of beneficiaries for PX4: 576 |  |  | KAP | Total # trained for indicator PX5: 156 | [6 empty] | Total # for indicator P6: 7
| Footnotes: 1 unit of each of the NFIs distributed per HH Units of NFIs to VDCS: 2mattress, 196 cloth, 1 kitchen utensil, 1 tarp, 4blanket - Byasi, VDC, Bhaktapur 1mattress, 1 kitchen utensil 4 tarps - Harisiddi VDC, Lalitpur 2blanket - Thaiba VDC, Lalitpur 22blanket-Motikhel VDC, Lalipur | [5 empty] | Footnotes: Kgs of Rice to VDCs: 325kg Rice - Harisiddi VDC, Lalitpur 790kg Rice - Byasi VDC, Bhaktapur 250kg Rice - Motikhel VDC, Lalitpur 50kg Rice - Thaiba VDC, Lalitpur Along with rice, food basket also contained Pulse, Oil & Salt 74kg Pulse, 37l oil, 37kg salt - Byasi VDC, Bhaktapur 21kg Pulse, 15l oil, 15kg salt - Harisiddi VDC, Lalitpur 1kg Pulse, 2l oil, 1kg salt - THaiba VDC, Lalitpur 10kg Pulse, 5l oil, 10 kg salt - Motikhel VDC, Lalitpur | Footnotes: Packets of Baby feed to VDCS: 65 - Byasi VDC, Bhaktapur 80 - Harisiddi VDC, Lalitpur 5 - Thaiba VDC, Lalitpur 10 - Motikhel VDC, Lalitpur | Footnotes: BR distribution data not included on totals. Packets of BR to VDCS: 2 - Byasi VDC, Bhaktapur 5 - Harisiddi VDC, Lalitpur 1 - Thaiba VDC, Lalitpur 10 - Motikhel VDC, Lalitpur | Footnotes: No. Of HH = No. of Beneficiaries / 5.5 Person

## POURAKHI (Dhading)
NERP file designed by Biju & updated as of 07.10.2015
District | Protection / Psychosocial Support (PSS)
| Indicator P1: 5,000 affected families/households have access to community based psychosocial support. ACT Target: 5000HH | [9 empty] | Indicator P2: Community and family support networks (formal and informal groups) that provide protection, care, and psychosocial support for vulnerable earthquake-affected families are strengthened. ACT Target: 25 |  |  |  |  | (Non ACT) Indicator P2X: Recorded # of network members for indicator P2 Target: tbc |  |  |  |  | Indicator P3: # of safe spaces for women and children established and equipped. ACT Target: tbc | Indicator P4: Culturally appropriate recreational activities for girls, boys and adolescents organized in affected communities. ACT Target: tbc |  |  | (Non ACT) Indicator PX4: Recorded # of beneficiaries for indicator P4 Target: tbc |  |  | Indicator P5: Increased levels of knowledge on CBPS among participants. ACT Target: tbc | (ACT member staff and community/social workers and staff of partners trained in community based psychosocial support and/or psychological first aid. Target: tbc |  |  | Indicator P6: Referral systems for people in need of focused care/specialized mental health or protection services identified/established ACT Target: ?
| Total # of Beneficiaries | Total # of sessions | # of individual counselling sessions | # of beneficiaries from individual counselling | # of family counselling sessions | # beneficiaries from of Family Counselling | # of group counselling sessions | # of beneficiaries from Group Counselling | # of motivational sessions & awareness on CBPS to school students | # of beneficiaries from Motivational Sessions & awareness on CBPS to school students | # of Networks Established | ToT to school teachers | Awareness & orientation to teachers on PSS | Awareness to youth groups on CBPS | Awareness & orientation on CBPS to women group | # of beneficiaries from ToT to school teachers | # of beneficiaries form Awareness & orientation to teachers on PSS | # of beneficiaries from Awareness to youth groups on CBPS | # of beneficaries orientation on CBPS to school students | # beneficiaries from Awareness & orientation on CBPS to women group | # of Spaces Established | RA for Women | RA for School Children | RA for Youth | # of beneficiaries from RA for women | # of beneficiaries from RA for school children | # of beneficiaries from RA for Youth | KAP | # of Partner staffs trained | # trained in training on CBPSS by Partner to community network | # trained in capacity building Capacity Building training to community network | # of people referred for PSS/Protection Issues
Dhading | 7548 | 155 | 15 | 341 | 13 | 93 | 81 | 4093 | 46 | 3021 | 3 | [5 empty] | 176 |  | 440 |  | 9 | 3 | 58 | 3 | 149 | 2091 | 201 | KAP | 7 | 31
| Total # of beneficiaries for indicator P1: 7548 | [9 empty] | Total networks formed for indicator P2: 3 |  |  |  |  | Total # of beneficiaries for indicator PX2: 616 |  |  |  |  | Total # of spaces created for indicator P3: 9 | Total # of activities conducted for indicator P4: 64 |  |  | Total # of beneficiaries for PX4: 2441 |  |  | KAp | Total # trained for indicator PX5: 38 |  |  | Total # for indicator P6: 0
Footnotes: No. Of HH = No. of Beneficiaries / 5.5 Person